## Progress Planning and Tracking
Project Name: | CCSE PMO Spring 2020
Report Date: | 2020-01-26
[5 empty] | Milestone #1 |  |  |  | Milestone #2 |  |  |  | Milestone #3
Deliverable | Tasks | Complete% | Current Status Memo | Assigned To | 2026-01-01 | 2002-02-01 | 2009-02-01 | 2016-02-01 | 2023-02-01 | 2001-03-01 | 2008-03-01 | 2015-03-01 | 2022-03-01 | 2029-03-01 | 2005-04-01 | 2012-04-01 | 2019-04-01 | 2026-04-01
Research | Interview users | 100% |  | Devin | 4
| Gather Data | 100% |  | Devin | 4
| Analyze Q&A | 100% |  | Syed, Wendy | 2
Database Design | Configuring workspace | 100% |  | Wendy | 5
| Creation of Table structure | 100% |  | Team | 10 | 5 | 4
| Creation of Database | 100% |  | Team |  | 10 | 10 | 3
| linking of required tables | 100% |  | Faith, Devin |  |  | 8 | 8 | 4
| Creation of report methods | 100% |  | Syed, Wendy |  |  |  | 8 | 8 | 4 | 4 | 2
| Testing | 100% |  | Syed, Devin |  | 5 | 5 |  | 6 | 4 | 8
| Documentation | 100% |  | Team |  |  | 4 | 4 | 4 | 3 | 5 | 10 |  |  | 4 | 2
GUI Implementaion | Determine GUI buttons | 100% |  | Devin |  |  |  | 6 | 4 | 4 | 2
| Creation of GUI | 100% |  | Devin, Wendy |  |  |  | 4 | 6 | 5 | 6 | 6 | 8
| Role based Access | 100% |  | Team | [5 empty] | 5 | 5 | 5 | 5 | 10 | 5
| Testing | 100% |  | Faith, Syed |  |  |  |  | 5 | 5 | 5 | 5 | 10 | 5 | 4 | 6 | 6 | 4
| Documentation | 100% |  | Team |  |  |  | 1 | 2 | 2 | 4 | 6 |  |  | 8 | 10
Final report | Creation of Powerpoint | 100% |  | Devin | [8 empty] | 5 | 5 | 10 | 2
| Creation of final report | 100% |  | Team | [8 empty] | 5 | 10 | 10 | 5 | 5
| Presentation preperation | 100% |  | Team | [11 empty] | 5 | 10 | 10
| Formal presentation | 100% |  | Syed, Devin,Wendy | [13 empty] | 10
| Final report submission | 100% |  | Devin | [13 empty] | 5
| Total workload | 438 |  |  | 25 | 20 | 31 | 34 | 39 | 32 | 39 | 34 | 33 | 30 | 41 | 30 | 21 | 29
Legend |  |  | This document is subject to change.
Planned | 2
Delayed | 1
Number | Workload: man hour